## Sprint i
ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Assigned | Names and Contribution Percentage
Artifact 1 | Create documentation | 1 | Create kanban board | 1 | Establish documentation, address feedback, establish requirements, begin implementation, and create ui mockup | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 1.1 | Create product backlog |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 1.2 | Create SRS document |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 1.3 | Create sprint backlog |  |  | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 1.4 | Put user stories in sprint backlog |  |  | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 1.5 | Put user stories in product backlog |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
Artifact 2 | Address feedback | 2 | Address and respond to feedback in product description doc |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 2.1 | Address and respond to feedback in user story doc |  |  | DOC | 1 | 1 | Emily | Emily 100%
Artifact 3 | Establish functional and nonfunctional requirements | 3 | Write nonfunctional requirements |  |  | DOC | 2 | 2 | All but Dean | Brianna 20%, Roisin 20%, Emily 40%, Sarah 20%
|  | 3.1 | Write functional requirements |  |  | DOC | 2 | 2 | All but Emily | Brianna 20%, Roisin 20%, Dean 40%, Sarah 20%
Artifact 4 | Begin impelemtation | 4 | Create actual implementation |  |  | GH | 2 | 2 | Brianna | Brianna 100%
|  | 4.1 | Update ReadMe file with download instructions |  |  | GH | 1 | 1 | Brianna | Brianna 100%
|  | 4.2 | Make current links document |  |  | GH | 1 | 1 | Brianna | Brianna 100%
Artifact 5 | UI mockup | 5 | UI mockup |  |  | UI | 3 | 3 | Roisin | Roisin 100%
Artifact 6 | Quality checking | 6 | Quality check sprint backlog |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 6.1 | Quality check product backlog |  |  | QC | 1 | 1 | Sarah | Sarah 100%
|  | 6.2 | Quality check user story feedback |  |  | QC | 1 | 1 | Roisin | Roisin 100%
|  | 6.3 | Quality check functional requirements |  |  | QC | 1 | 1 | Emily | Emily 100%
|  | 6.4 | Quality check feedback in product description |  |  | QC | 1 | 1 | Dean | Dean 100%
|  | 6.5 | Quality check nonfunctional requirements |  |  | QC | 1 | 1 | Dean | Dean 100%
Artifact 7 | Upkeep Documentation | 7 | Handle necessary upkeep/updates on product backlog | 2 | Upkeep documentation, improve UI mockups, begin implementation, and quality check work | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 7.1 | Make architecture design doc |  |  | DOC | 1 | 1 | Emily | Emily 100%
|  | 7.2 | Fill in SRS document section 1 and 2 |  |  | DOC | 1 | 1 | Emily, Dean | Emily 50%, Dean 50%
|  | 7.3 | Handle necessary upkeep/updates on sprint backlog |  |  | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 7.4 | Make use case diagrams |  |  | DOC | 2 | 2 | Brianna, Sarah | Brianna 66%, Sarah 34%
|  | 7.5 | Make use case descriptions |  |  | DOC | 2 | 2 | Brianna, Sarah | Brianna 66%, Sarah 34%
|  | 7.6 | Add quality checking policy to wiki |  |  | GH | 1 | 1 | Brianna | Brianna 100%
|  | 7.7 | Improve requirements in the SRS doc |  |  | DOC | 1 | 1 | Dean, Brianna | Dean 50%, Brianna 50%
Artifact 8 | UI Mockups | 8 | Address feedback specific to ui mockups |  |  | UI | 1 | 1 | Roisin | Roisin 100%
|  | 8.1 | Make improvements on UI mockups |  |  | UI | 1 | 1 | Roisin | Roisin 100%
|  | 8.2 | Sleep Tracker Mockup |  |  | UI | 1 | 1 | Roisin | Roisin 100%
User Story 3 | As a user, I want the user interface of the application to be readable, easy to understand, and uses inviting language so that I am not distracted from my progress by frustration from navigating a difficult or harsh interface. | 3 | Implement Homepage |  |  | IM | 3 | 3 | Emily, Sarah, Brianna | Emily 33%, Sarah 33%, Brianna 33%
|  | 3.1 | React's routing features |  |  | IM | 3 | 3 | Emily, Brianna | Emily 50%, Brianna 50%
Artifact 9 | Quality checking | 9 | Quality check sprint backlog |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 9.1 | Quality check product backlog |  |  | QC | 1 | 1 | Sarah | Sarah 100%
|  | 9.2 | Quality check use case diagrams |  |  | QC | 1 | 1 | Brianna, Sarah | Brianna 50%, Sarah 50%
|  | 9.3 | Quality check use case descriptions |  |  | QC | 1 | 1 | Brianna, Sarah | Brianna 50%, Sarah 50%
|  | 9.4 | Quality check Architecture Design Doc |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 9.5 | Quality check SRS document section 1 and 2 |  |  | QC | 1 | 1 | Emily, Dean | Emily 50%, Dean 50%
Artifact 10 | Upkeep Documentation | 10 | Maintain sprint backlog | 3 | Upkeep documentation, improve UI mockups, make progress on navigation, display, and back end, and quality check work | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 10.1 | Maintain product backlog |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 10.2 | Domain Model |  |  | DOC | 2 | 2 | Emily | Emily 100%
|  | 10.3 | Fill in rest of SRS document section 3 |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 10.4 | Fill in SRS document section 6 |  |  | DOC | 1 | 1 | Dean | Dean 100%
|  | 10.5 | Fill in parts of SRS document section 4 |  |  | DOC | 1 | 1 | Dean | Dean 50%, Brianna 50%
|  | 10.6 | Update Architecture Design document if necessary |  |  | DOC | 1 | 1 | Emily | Emily 100%
Artifact 11 | Address feedback | 11 | Address feedback on and maintain Use Case Descriptions and Diagrams |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 11.1 | Address feedback on Architecture Design document |  |  | DOC | 1 | 1 | Emily | Emily 100%
Artifact 12 | UI | 12 | Update UI mockups based on Usability Testing |  |  | UI | 1 | 1 | Roisin | Roisin 100%
User Story 3/ User Story 6 | As a user, I want the user interface of the application to be readable, easy to understand, and uses inviting language so that I am not distracted from my progress by frustration from navigating a difficult or harsh interface. As a user, I want the application to feel fun, friendly and inviting, so that using the application feels rewarding and helps to build self-confidence. | 3.0/6.0 | Implement navigation functionality |  |  | IM | 2 | 2 | Emily, Sarah, Dean | Emily 50%, Sarah 50%
|  | 3.1/6.1 | Implement Registration page (firebase) |  |  | IM | 3 | 3 | Emily | Emily 100%
|  | 3.2/6.2 | Implement Homepage/Avatarpage |  |  | IM | 3 | 3 | Sarah | Sarah 100%
|  | 3.3/6.3 | Begin task implementation |  |  | IM | 3 | 3 | Emily, Sarah, Dean | Sarah 100%
Artifact 13 | Implementation (not user story specific) | 13 | Record implementation video |  |  | DOC | 2 | 2 | Sarah | Sarah 100%
|  | 13.1 | Continuous Integration |  |  | IM | 2 | 2 | Brianna | Brianna 100%
Artifact 14 | Quality Checking | 14 | Quality check sprint backlog |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 14.1 | Quality check product backlog |  |  | QC | 1 | 1 | Sarah | Sarah 100%
|  | 14.2 | Quality check section 3 of SRS document |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 14.3 | Quality check section 4 of SRS document |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 14.4 | Quality check new/updated ui mockups |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 14.5 | Quality check section 6 of SRS document |  |  | QC | 1 | 1 | Roisin | Roisin 100%
|  | 14.6 | Quality check domain model |  |  | QC | 1 | 1 | Dean | Brianna 100%
|  | 14.7 | Quality check use case diagram feedback |  |  | QC | 1 | 1 | Emily | Emily 100%
Artifact 15 | Upkeep Documentation and UI Mockups | 15 | Maintain product backlog | 4 | Upkeep documentation, improve UI mockups, make progress on task functionality, avatar display, organization, and back end, and quality check work | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 15.1 | Maintain sprint backlog |  |  | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 15.2 | Fill in the tables at the bottom of assignment descriptor |  |  | DOC | 1 | 1 | Emily | Emily 100%
|  | 15.3 | Handle Round 2 of Usability Testing (3 people) |  |  | DOC | 2 | 2 | Dean | Dean 70%, Brianna 30%
|  | 15.4 | Update UI mockups if necessary from usability testing |  |  | UI | 1 | 1 | Roisin | Roisin 100%
Artifact 16 | Design patterns and models | 16 | Make design pattern in technical design document |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 16.1 | Handle technical design pattern in domain model doc |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 16.2 | Detailed design model for registration page in domain model doc |  |  | DOC | 1 | 1 | Emily | Emily 100%
|  | 16.3 | Detailed design model for sign-in page in domain model doc |  |  | DOC | 1 | 1 | Dean | Dean 100%
|  | 16.4 | Detailed design model for avatar page in domain model doc |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 16.5 | Detailed design model for tasks page in domain model doc |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
Artifact 17 | Address Feedback | 17 | Get feedback from Dr. Greg on usability testing script |  |  | DOC | 1 | 1 | Dean | Dean 100%
|  | 17.1 | Respond to feedback on Domain Model |  |  | DOC | 1 | 1 | Emily | Emily 100%
|  | 17.2 | Address feedback from Dr. Greg |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
Artifact 18 | Quality Checking | 18 | Quality check sprint backlog |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 18.1 | Quality check usability testing report |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 18.2 | Quality check technical design in domain model document |  |  | QC | 1 | 1 | Roisin | Roisin 100%
|  | 18.3 | Quality check design pattern in domain model doc |  |  | QC | 1 | 1 | Roisin | Roisin 100%
|  | 18.4 | Quality check updated UI mockups if necessary |  |  | QC | 1 | 1 | Dean | Dean 100%
|  | 18.5 | Quality check product backlog |  |  | QC | 1 | 1 | Sarah | Sarah 100%
User Story 7 | As a user, I want to feel attached to my avatar and help it grow so that it encourages me to take better care of myself. | 7 | Avatar Page implementation |  |  | IM | 3 | 3 | Brianna | Brianna 100%
|  | 7.1 | Create Avatar options |  |  | IM | 2 | 2 | Sarah | Sarah 100%
User Story 15 | As a user, I want to know if my stored data is secure so I can feel confident in sharing/storing personal information. | 15 | Implement Firebase for backend |  |  | IM | 3 | 3 | Emily, Dean, Roisin | Emily 33%, Dean 33%, Roisin 33%
|  | 15.1 | Implement Sign up/Log in classes |  |  | IM | 3 | 3 | Emily, Dean, Roisin | Emily 33%, Dean 33%, Roisin 33%
User Story 12/ User Story 17 | As a user, I want to efficiently organize my tasks by category and topic to keep track of my due dates. As a user, I want to automatically renew tasks, by selecting a daily/weekly option when the task is created so that repeat tasks are easy to set up and use. | 12.0/17.0 | Modify the pages meant to display tasks |  |  | IM | 2 | 2 | Sarah | Sarah 100%
|  | 12.1/17.1 | Implement Add Task CSS |  |  | IM | 3 | 3 | Roisin | Roisin 100%
|  | 12.2/17.2 | Implement Add Task functionality to task page |  |  | IM | 3 | 3 | Emily | Emily 100%
|  | 12.3/17.3 | Organize current code |  |  | IM | 3 | 3 | Dean | Dean 100%
Artifact 19 | Upkeep Documentation and UI Mockups | 19 | Maintain sprint backlog | 5 | Upkeep documentation, improve UI mockups if necessary, quality check work, and make progress on task functionality and display, avatar customization and display, earning and using points, and saving information to back end. | DOC | 1 | 1 | Sarah | Sarah 100%
|  | 19.1 | Maintain product backlog |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 19.2 | Update class design diagram pertaining to the avatar page |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 19.3 | Update ui mockups if necessary |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 19.4 | Maintain design pattern in class diagram doc |  |  | DOC | 1 | 1 | Roisin | Roisin 100%
|  | 19.5 | Fill out tables for deliverable 5 |  |  | DOC | 1 | 1 | Emily | Emily 100%
|  | 19.6 | Update class design diagram pertaining to the task page |  |  | DOC | 1 | 1 | Emily | Emily 100%
|  | 19.7 | Update class design diagram pertaining to firebase and backend (if necessary) |  |  | DOC | 1 | 1 | Dean | Dean 100%
Artifact 20 | Usability testing and Addressing Feedback | 20 | Do usability testing write-up for round 3 of usability testing |  |  | DOC | 1 | 1 | Brianna | Brianna 100%
|  | 20.1 | Do usability testing with one person |  |  | DOC | 3 | 3 | All | Brianna 20%, Sarah 20%, Emily 20%, Dean 20%, Roisin 20%
|  | 20.2 | Address feedback from Dr. Greg |  |  | DOC | 1 | 1 | Emily | Emily 100%
Artifact 21 | Quality Checking | 21 | Quality check sprint backlog |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 21.1 | Quality check updated ui mockups |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 21.2 | Quality check usability test surveys |  |  | QC | 1 | 1 | Brianna | Brianna 100%
|  | 21.3 | Quality Check updated class design diagram document |  |  | QC | 1 | 1 | Dean | Brianna 100%
|  | 21.4 | Quality check product backlog |  |  | QC | 1 | 1 | Sarah | Sarah 100%
User Story 2 | 2. As a user, I want the application to recognize when I’m developing positive habits and maintaining consistency so that I can be rewarded for my progress and stay motivated. 7. As a user, I want to feel attached to my avatar and help it grow so that it encourages me to take better care of myself. 14. As a user, I want to be able to set a schedule/routine for friendly and supportive reminders so that I don’t forget to do basic tasks like making/eating lunch. 16. As a user, I want to have AI suggest tasks automatically based on previous tasks to save time setting up tasks. 22. Non user stoy implementation. | 2 | Work on populating the homepage with information on other pages |  |  | IM | 3 | 2 | Emily, Roisin, Dean | Emily 33%, Roisin 33%
|  | 2.1 | Finish work on backend implementation |  |  | IM | 2 | 1 | Dean | Dean 50%
|  | 2.2 | Work on implementing point rewards for completing tasks |  |  | IM | 2 | 2 | Roisin | Roisin 100%
|  | 2.3 | Implement the purchasing of customization options |  |  | IM | 2 | 2 | Roisin | Roisin 100%
User Story 7 |  | 7.2 | Handle avatar customization functionality |  |  | IM | 3 | 3 | Brianna | Brianna 100%
|  | 7.3 | Finish drawings for avatar customization |  |  | IM | 3 | 3 | Sarah | Sarah 100%
User Story 14 |  | 14 | Finish up the task implementation on task page |  |  | IM | 3 | 3 | Emily | Emily 100%
User Story 16 |  | 16 | Work on the use of AI to recommend tasks for a given goal |  |  | IM | 2 | 2 | Dean | Dean 100%,
Artifact 22 |  | 22 | Write tests for pages for added coverage |  |  | IM | 2 | 2 | Sarah | Sarah 100%
|  | 22.1 | Record implementation video for dev 5 |  |  | IM | 1 | 1 | Sarah | Sarah 100%

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657